## Gantt Chart
GANTT CHART
PROJECT TITLE
PROJECT MANAGER | [6 empty] | DATE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
 | time axis 2025-07-27 to 2026-12-10
 | time axis 2025-07-27 to 2026-12-10
1 | Project Initiation & Proposal Phase | bar: 2025-07-27 to 2025-09-24
1.1 | Selecting the research problem | Isuru | 2025-07-27 | 2025-08-02 | 7 | finished
1.2 | Getting the approval of the research problem | Isuru | 2025-08-02 | 2025-08-09 | 8 | finished
1.3 | Do the literature Survey | Isuru | 2025-08-09 | 2025-09-20 | 43 | finished
1.4 | Project proposal Chapter 1 | Isuru | 2025-08-20 | 2025-09-07 | 19 | finished
2 | Project proposal chapter 3 | Isuru | 2025-09-30 | 2025-09-30 | 1 | finished
2.1 | LS - Restructuring and preparing for LR | Isuru | 2025-09-15 | 2025-09-16 | 2 | finished
2.2 | Proposal Chapter 2 (LR) | Isuru | 2025-09-17 | 2025-09-19 | 3 | finished
2.3 | Supervisor Review On Draft Proposal | Isuru | 2025-09-19 | 2025-09-23 | 5 | finished
2.4 | Proposal Improvements & Self Evaluation | Isuru | 2025-09-24 | 2025-10-07 | 14 | finished
3 | Proposal Submission - initial draft | Isuru | 2025-09-26 | 2025-10-10 | 15 | finished
3.1 | Explore more on the requirements | Isuru | 2025-10-09 | 2025-10-10 | 2 | finished
3.2 | Preparing the questionairs | Isuru | 2025-10-10 | 2025-10-10 | 1 | finished
3.3 | Distributing questionairs | Isuru | 2025-10-10 | 2025-10-15 | 6 | finished
4 | Documenting the findings and making notes | Isuru | 2025-10-15 | 2025-10-15 | 1 | finished
4.1 | Creating the SRS | Isuru | 2025-10-16 | 2025-10-19 | 4 | finished
4.2 | Getting Supervisor Feedback on SRS | Isuru | 2025-10-19 | 2025-11-08 | 21 | finished
4.3 | SRS Improvements & self evaluation | Isuru | 2025-10-22 | 2025-11-13 | 23 | finished
5 | Proposal and Requirement Final Draft Submission | Isuru | 2025-11-13 | 2025-11-13 | 1 | finished
5 | Self Evaluation in final draft (proposal & SRS) | Isuru | 2025-11-14 | 2025-11-20 | 7 | finished
5 | Final Submission of Proposal & SRS | Isuru | 2025-11-20 | 2025-11-20 | 1 | finished
5 | Creating architecture Design for the project | Isuru | 2025-11-01 | 2025-11-04 | 4 | finished
5 | Getting Supervisor Review | Isuru | 2025-11-20 | 2025-11-21 | 2 | finished
5 | Creating the design of the system (UI & Wireframes) | Isuru | 2025-11-21 | 2025-11-25 | 5 | finished
5 | Finalising the Design Section | Isuru | 2025-11-19 | 2025-11-26 | 8 | finished
5 | Getting Supervisor Review & feedback | Isuru | 2025-11-26 | 2025-11-30 | 5 | finished
5 | Self Evaluation & improvements | Isuru | 2025-11-30 | 2025-12-02 | 3 | finished
5 | Technology selections | Isuru | 2025-08-02 | 2025-09-14 | 44 | finished
5 | Dataset Selections | Isuru | 2025-08-02 | 2025-09-14 | 44 | finished
5 | Data Augmentation | Isuru | 2025-12-05 | 2025-12-12 | 8 | finished
5 | Core Feature Implementations | Isuru | 2025-10-26 | 2025-12-20 | 56 | finished
5 | Implementing other improvements | Isuru | 2025-12-21 | 2025-12-24 | 4 | finished
5 | Getting Supervisors Feedback by presenting | Isuru | 2025-12-25 | 2025-12-30 | 6 | finished
5 | Self Evaluation and refinements | Isuru | 2025-12-30 | 2026-01-02 | 4 | finished
5 | Prototype Submission | Isuru | 2026-01-02 | 2026-01-02 | 1 | finished
5 | Identification of Functional & Non-functional req | Isuru | 2026-01-03 | 2026-01-04 | 2 | finished
5 | Creating the test plan & Execution | Isuru | 2026-01-05 | 2026-01-10 | 6 | finished
5 | Overall Evaluation prototype | Isuru | 2026-01-11 | 2026-01-15 | 5 | finished
5 | Finalizing the Testing report & Evaluation | Isuru | 2026-01-16 | 2026-01-22 | 7 | Started
5 | Drafting the final research | Isuru | 2026-01-23 | 2026-02-25 | 34 | Started
5 | Supervisor Review | Isuru | 2026-02-26 | 2026-03-18 | 21
5 | Improvements & self evaluation | Isuru | 2026-03-19 | 2026-03-31 | 13
5 | Final Submission | Isuru | 2026-04-01 | 2026-04-01 | 1
5 | Final Presentation & Viva | Isuru | 2026-04-01 | 2026-04-01 | 1
| MVP | Isuru | 2026-04-01 | 2026-04-01 | 1
| Learn basic python & polish basic knowledge | Isuru | 2025-08-13 | 2025-08-13 | 1
| work on Numpy | Isuru | 2025-09-14 | 2025-09-15 | 2
| work on Pandas | Isuru | 2025-09-15 | 2025-09-17 | 3
| ML Fundamentals-scikit-learn | Isuru | 2025-11-03 | 2025-11-12 | 10
| Tensors | Isuru | 2025-11-12 | 2025-11-14 | 3
| NN | Isuru | 2025-11-14 | 2025-11-16 | 3
| CNNS | Isuru | 2025-11-17 | 2025-11-20 | 4
| OpenCV & MediaPipe | Isuru | 2025-11-20 | 2025-11-22 | 3
| Knowledge in NLP | Isuru | 2025-11-22 | 2025-11-26 | 5
| Self Evaluation | Isuru | 2025-11-26 | 2025-12-31 | 36
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1